## TestCase
Project Name: |  | Qtec Solution Website Testing (Task 01)
Test URL: |  | https://staging.qtecsolution.com/
Tester Name: |  | MD Mahedy hasan Naiem
Test Date: |  | 28-Mar-2026
Environment: |  | Staging ¦ Web
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers without any layout or functional issues. | Found as per expectation. | Browsers - Chrome, Mozilla Firefox, Microsoft Edge, Safari. | 1. Go to different browsers. 2. Search the URL. 3. Go to the website https://staging.qtecsolution.com/ |  |  | Passed
2 | Navigation Bar | Functional | Navigation | Verify all navigation menu links are clickable and redirect to the correct pages. | Each nav link should load the correct page without any error. | Found as per expectation. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Click on each navigation menu link one by one. 3. Check if the correct page loads. |  |  | Passed
3 | Navigation Bar | Functional | Navigation | Verify the Services dropdown menu appears and all sub-links work correctly. | Services dropdown should open. All sub-links should redirect to correct service pages. | Dropdown opens on Chrome and Firefox. Dropdown appears behind page content on Safari. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Hover over the "Services" menu item. 3. Click each dropdown sub-link and check if correct page loads. | SS_BUG_01_Services_Dropdown_Safari.png |  | Failed | Safari z-index issue
4 | Navigation Bar | Functional | Navigation | Verify the hamburger menu icon appears on mobile and opens the nav menu when tapped. | Hamburger icon should appear on mobile viewport and open the menu when tapped. | Found as per expectation. | Viewport: 375px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 375px. 3. Check if hamburger icon appears. 4. Tap the icon and verify menu opens. | SS_BUG_02_Hamburger_Menu_Open.png |  | Passed
5 | Navigation Bar | Functional | Navigation | Verify the hamburger menu closes when user taps outside the menu panel. | Menu should close when user taps anywhere outside the menu panel on mobile. | Menu remains open when tapping outside. Close only works via the X icon. | Viewport: 375px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 375px. 3. Tap the hamburger icon to open menu. 4. Tap anywhere outside the menu panel. | SS_BUG_03_Hamburger_Outside_Tap.png |  | Failed | Menu not closing on outside tap
6 | Navigation Bar | Functional | Navigation | Verify the Services dropdown is accessible via keyboard navigation (Tab + Enter). | Tab key should navigate to Services link and pressing Enter should open the dropdown. | Pressing Enter on Services does not open the dropdown via keyboard. | Keyboard only navigation | 1. Go to the URL https://staging.qtecsolution.com/ 2. Use Tab key to focus on the Services nav link. 3. Press Enter and check if dropdown opens. | SS_BUG_04_Keyboard_Nav_Services.png |  | Failed | Keyboard accessibility issue
7 | Navigation Bar | Functional | Navigation | Verify active page is visually highlighted in the navigation bar. | Current page link should look different from other links (underline or color change). | All navigation links look identical. No active state applied to current page. | None | 1. Go to the URL https://staging.qtecsolution.com/about-us 2. Check if "About Us" link is highlighted differently in the navbar. | SS_BUG_05_Nav_Active_State.png |  | Failed
8 | Contact Form | Function | Contact | Verify contact form submits successfully with all valid inputs. | Form should submit and show a success message "Your message has been sent". | No success or failure message shown after clicking Send. | Name: Test User Email: test@gmail.com Message: Hello | 1. Go to the URL https://staging.qtecsolution.com/contact-us 2. Fill all fields with valid data. 3. Select a budget option. 4. Click "Send". | SS_BUG_06_No_Success_Message.png |  | Failed | No success message
9 | Contact Form | Function | Contact | Verify the Name field shows error when left blank. | Should show a pop-up error message "Name is required". | No validation error shown. Form submits silently with empty Name. | Left the Name field blank. | 1. Go to the URL https://staging.qtecsolution.com/contact-us 2. Leave the Name field blank. 3. Fill other fields with valid data. 4. Click "Send". | SS_BUG_07_Name_Blank_Validation.png |  | Failed
10 | Contact Form | Function | Contact | Verify the Email field shows error when left blank. | Should show a pop-up error message "Email is required". | No validation error shown. Form submits silently with empty Email. | Left the Email field blank. | 1. Go to the URL https://staging.qtecsolution.com/contact-us 2. Leave the Email field blank. 3. Fill other fields with valid data. 4. Click "Send". | SS_BUG_08_Email_Blank_Validation.png |  | Failed
11 | Contact Form | Function | Contact | Verify the Email field shows error when invalid email format is entered. | Should show a pop-up error message "Please enter a valid email address". | Form proceeds without any email format validation error. | Email: test@ | 1. Go to the URL https://staging.qtecsolution.com/contact-us 2. Enter "test@" in the Email field. 3. Fill other fields with valid data. 4. Click "Send". | SS_BUG_09_Invalid_Email_Format.png |  | Failed
12 | Contact Form | Function | Contact | Verify the Message field shows error when left blank. | Should show a pop-up error message "Message is required". | No validation error shown. Form submits silently with empty Message. | Left the Message field blank. | 1. Go to the URL https://staging.qtecsolution.com/contact-us 2. Leave the Message field blank. 3. Fill other fields with valid data. 4. Click "Send". | SS_BUG_10_Message_Blank_Validation.png |  | Failed
13 | Contact Form | Function | Contact | Verify the Budget dropdown shows all options and each option can be selected. | All 4 budget options should be visible and selectable from the dropdown. | Found as per expectation. | None | 1. Go to the URL https://staging.qtecsolution.com/contact-us 2. Click the Budget dropdown. 3. Check all 4 options are visible and selectable. |  |  | Passed
14 | All Pages | Functional | Navigation | Verify page redirections and URL correctness for all main pages. | Each page should load with the correct URL. No unexpected redirects. | Found as per expectation. | None | 1. Manually visit /, /about-us, /case-studies, /services, /contact-us, /blog. 2. Verify each URL is correct and page loads without error. |  |  | Passed
15 | All Pages | Functional | Navigation | Verify browser back and forward button navigation works correctly on all pages. | Should navigate correctly between pages without any error. | Found as per expectation. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Navigate to About Us then Services. 3. Click browser back button. 4. Click browser forward button. |  |  | Passed
16 | All Pages | Functional | Search | Verify search functionality is available and works properly (if available). | If search exists it should return relevant results. If absent no search elements should mislead users. | No search functionality found on any page. Noted as observation. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Check all pages for a search bar or search icon. 3. If found test with valid and invalid queries. |  |  | Passed | Search not available on this site
17 | Contact Form | Function | Contact | Verify "Book on Calendar" link opens Calendly booking page in a new tab. | Should open the Calendly booking page in a new browser tab. | Found as per expectation. | None | 1. Go to the URL https://staging.qtecsolution.com/contact-us 2. Click the "Book on Calendar" link next to the Send button. |  |  | Passed
18 | Footer | Functional | Footer Links | Verify footer "About Us" link redirects to the About Us page. | Should redirect to the About Us page. | Found as per expectation. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Scroll to the footer. 3. Click the "About Us" link. |  |  | Passed
19 | Footer | Functional | Footer Links | Verify footer "Articles" link redirects to the Articles page. | Should redirect to the Articles page without error. | Clicking "Articles" link shows a 404 Not Found error page. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Scroll to the footer. 3. Click the "Articles" link. | SS_BUG_11_Footer_Articles_404.png |  | Failed | 404 error
20 | Footer | Functional | Footer Links | Verify footer social media icon links open correct platforms in new tab. | Each social media icon should open the correct social platform in a new browser tab. | Found as per expectation. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Scroll to the footer. 3. Click each social media icon one by one. |  |  | Passed
21 | Footer | Functional | Footer Links | Verify footer newsletter Subscribe shows error for blank or invalid email. | Should show a validation error "Please enter a valid email address". | No error shown. Subscribe button does nothing or page reloads silently. | Left the email field blank. | 1. Go to the URL https://staging.qtecsolution.com/ 2. Scroll to the footer. 3. Leave the email field blank. 4. Click "Subscribe". | SS_BUG_12_Footer_Subscribe_No_Validation.png |  | Failed
22 | Footer | Functional | Footer Links | Verify Privacy Policy and Terms & Conditions links are present in the footer. | Both Privacy Policy and Terms & Conditions links should be visible in the footer. | Neither link found anywhere in the footer or on the site. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Scroll to the footer. 3. Look for Privacy Policy and Terms & Conditions links. | SS_BUG_13_Missing_Privacy_Terms.png |  | Failed | Links missing
23 | Homepage | Functional | Links | Verify "Explore Our Works" button scrolls to the projects section. | Should smoothly scroll down to the projects/portfolio section on the homepage. | Scroll behavior is abrupt. Anchor link not properly aligned to the section. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Click the "Explore Our Works" button in the hero section. | SS_BUG_14_Explore_Anchor_Scroll.png |  | Failed
24 | Homepage | Functional | Links | Verify "View Portfolio" button opens the portfolio in a new tab. | Should open the Qtec portfolio page in a new browser tab. | Found as per expectation. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Click the "View Portfolio" button. |  |  | Passed
25 | Homepage | UI | Alignment | Verify alignment of all elements (headers, text, images, buttons) on homepage. | All elements should be properly aligned with consistent margins and spacing. | Found as per expectation. | Viewport: 1366px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Check hero section alignment. 3. Check service cards alignment. 4. Check stats and testimonials section. |  |  | Passed
26 | All Pages | UI | Font & Color | Verify font consistency, color scheme and branding alignment across all pages. | Same font family and brand colors should be used consistently across all pages. | Font family consistent. CTA button styles vary across pages. Brand color mostly consistent. | Chrome vs Firefox | 1. Open all main pages in Chrome. 2. Check font family, sizes and brand color (#1A6B3C or similar). 3. Compare heading styles across pages. | SS_BUG_15_Inconsistent_Button_Styles.png |  | Failed
27 | All Pages | UI | Spacing | Verify spacing, padding and margin are correct on different screen resolutions. | Consistent and correct spacing at all breakpoints. No collapsed or excessive spacing. | Spacing mostly appropriate. At 320px margins collapse. At 1920px some sections appear too wide. | Test at 320px, 768px, 1366px, 1920px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 320px and check element spacing. 3. Repeat at 768px, 1366px and 1920px. 4. Check for collapsed or excessive spacing. | SS_BUG_16_Spacing_320px.png |  | Failed | Spacing issue at extreme breakpoints
28 | Service Cards | UI | Buttons | Verify "Discuss for your project" buttons show a visible hover state. | Button should change color, background or show shadow effect on mouse hover. | No visual change on hover. Button looks identical in normal and hover state. | None | 1. Go to the URL https://staging.qtecsolution.com/ 2. Scroll to the Services section. 3. Hover mouse over the "Discuss for your project" button. | SS_BUG_17_Button_No_Hover_State.png |  | Failed
29 | All Pages | UI | Buttons | Verify CTA button styles (hover, active, disabled states) are consistent across pages. | All primary CTA buttons should have same color, size and border radius on all pages. | Button styles differ across homepage, contact page and service sub-pages. | None | 1. Note CTA button style on homepage. 2. Check "Send" button on /contact-us. 3. Check CTA buttons on service pages. 4. Compare all three. | SS_BUG_18_Inconsistent_CTA_Buttons.png |  | Failed
30 | All Pages | UI | Images | Verify all images scale properly and maintain clarity on all devices. | Images should scale proportionally, maintain aspect ratio and remain clear at all sizes. | Hero image scales well. Service images distort at 1024px tablet viewport. | Test at 320px, 768px, 1024px, 1366px | 1. Go to the URL https://staging.qtecsolution.com/services 2. Set viewport to 1024px. 3. Check service section images for distortion. | SS_BUG_19_Image_Distort_1024px.png |  | Failed
31 | All Pages | Responsive Testing | Responsive | Verify full page layout is correct at 320px mobile viewport. | No horizontal scroll. All elements within viewport. No broken layout. | Hero text overflows outside container. Floating CTA buttons overlap page content. | Viewport: 320px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 320px. 3. Scroll through all sections. | SS_BUG_20_Hero_Overflow_320px.png |  | Failed
32 | All Pages | Responsive Testing | Responsive | Verify full page layout is correct at 375px mobile viewport. | All content should fit. Footer columns should stack into a single column. | Footer columns overlap each other. Layout is broken at 375px. | Viewport: 375px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 375px. 3. Scroll to the footer. | SS_BUG_21_Footer_Overlap_375px.png |  | Failed
33 | All Pages | Responsive Testing | Responsive | Verify full page layout is correct at 414px mobile viewport. | All sections should be visible. Video section cards should be swipeable. | Video section cards are clipped. No swipe gesture or navigation arrows present. | Viewport: 414px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 414px. 3. Scroll to the video section. 4. Try swiping the cards. | SS_BUG_22_Video_Cards_414px.png |  | Failed
34 | All Pages | Responsive Testing | Responsive | Verify full page layout is correct at 768px tablet viewport. | No horizontal overflow. All sections should fit within the 768px width. | Testimonials section causes horizontal overflow at 768px. | Viewport: 768px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 768px. 3. Scroll to the testimonials section. | SS_BUG_23_Testimonials_Overflow_768px.png |  | Failed
35 | All Pages | Responsive Testing | Responsive | Verify full page layout is correct at 1024px tablet viewport. | All images should maintain correct aspect ratio. No distortion. | Service page images appear stretched and distorted at 1024px. | Viewport: 1024px | 1. Go to the URL https://staging.qtecsolution.com/services 2. Set viewport to 1024px. 3. Check service section images. | SS_BUG_24_Service_Image_Distort_1024px.png |  | Failed
36 | All Pages | Responsive Testing | Responsive | Verify full page layout is correct at 1366px desktop viewport. | Full desktop layout renders as designed. No layout issues. | Found as per expectation. | Viewport: 1366px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 1366px. 3. Scroll through all pages. |  |  | Passed
37 | All Pages | Responsive Testing | Responsive | Verify full page layout is correct at 1920px desktop viewport. | Content should be centered within max-width. No extreme stretching. | Found as per expectation. | Viewport: 1920px | 1. Go to the URL https://staging.qtecsolution.com/ 2. Set viewport to 1920px. 3. Check if content is properly centered. |  |  | Passed
38 | All Pages | Browser Compatibility Testing | Cross-Browser | Verify website works correctly in Google Chrome. | Site should be fully functional and correctly displayed in Chrome. | Found as per expectation. | Browser: Chrome (latest) | 1. Open https://staging.qtecsolution.com/ in Chrome. 2. Test all navigation links, contact form and footer. |  |  | Passed
39 | All Pages | Browser Compatibility Testing | Cross-Browser | Verify website works correctly in Mozilla Firefox. | Site should be fully functional and visually consistent with Chrome. | Headings appear lighter and thinner in Firefox compared to Chrome. | Browser: Firefox (latest) | 1. Open https://staging.qtecsolution.com/ in Firefox. 2. Test navigation, forms and compare font rendering with Chrome. | SS_BUG_25_Firefox_Font_Rendering.png |  | Failed | Font rendering issue
40 | All Pages | Browser Compatibility Testing | Cross-Browser | Verify website works correctly in Microsoft Edge. | Site should be fully functional and correctly displayed in Edge. | Found as per expectation on Chromium Edge. | Browser: Edge (latest) | 1. Open https://staging.qtecsolution.com/ in Edge. 2. Test navigation, contact form and footer. |  |  | Passed
41 | All Pages | Browser Compatibility Testing | Cross-Browser | Verify website works correctly in Apple Safari. | Site should be fully functional and correctly displayed in Safari. | Services dropdown appears behind hero section in Safari. Z-index issue found. | Browser: Safari (macOS) | 1. Open https://staging.qtecsolution.com/ in Safari. 2. Test navigation dropdown, images and contact form. | SS_BUG_26_Safari_Dropdown_Zindex.png |  | Failed | z-index issue
42 | All Pages | Performance Testing | Performance | Check page load speed using Lighthouse on mobile device. | Performance score should be 90+. FCP should be under 1.8s. TBT under 200ms. | Score: ~52. FCP: 4.2s. TBT: ~600ms. All Core Web Vitals fail. | Chrome DevTools > Lighthouse > Mobile | 1. Open https://staging.qtecsolution.com/ in Chrome. 2. Open DevTools > Lighthouse tab. 3. Select Mobile and Performance. 4. Click "Analyze page load". 5. Note the score and metrics. | SS_BUG_27_Lighthouse_Score_Mobile.png |  | Failed
43 | All Pages | Performance Testing | Performance | Verify images below the fold are lazy loaded on scroll. | Below-fold images should only load when the user scrolls near them. | All images load on initial page load. No lazy loading implemented. | Chrome DevTools > Network > Img filter | 1. Open https://staging.qtecsolution.com/ in Chrome. 2. Open DevTools > Network tab. 3. Filter by "Img". 4. Reload the page and observe that all images load at once. | SS_BUG_28_No_Lazy_Loading.png |  | Failed
44 | All Pages | Performance Testing | Performance | Check for JavaScript console errors on page load. | Zero console errors should appear on a clean page load. | 3 JS runtime errors and 1 resource 404 error found on every page load. | Chrome DevTools > Console | 1. Open https://staging.qtecsolution.com/ in Chrome. 2. Open DevTools > Console tab. 3. Reload the page. 4. Count all errors shown. | SS_BUG_29_Console_JS_Errors.png |  | Failed
45 | All Pages | Performance Testing | Performance | Verify WebP images have a JPEG or PNG fallback for older browsers. | Images should display correctly on all browsers including Safari iOS < 14. | WebP images served with no fallback. Images broken on Safari iOS 13. | Browser: Safari iOS 13 | 1. Open the site on Safari iOS 13. 2. Navigate to the homepage and services page. 3. Check if all images load correctly. | SS_BUG_30_WebP_No_Fallback_Safari.png |  | Failed

## Bug Report
Bug Reporting
# SL 01
Issue: Contact form submits with all fields blank. No validation error shown.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/contact-us 2. Leave all fields blank (Name, Email, Message). 3. Click the "Send" button.
Env: Staging
Module: Contact Form
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_07_Name_Blank_Validation.png
Expected: Should show inline validation errors for all required fields. Form should not submit.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 02
Issue: Invalid email format "test@" accepted in contact form without any validation error.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/contact-us 2. Enter "test@" in the Email field. 3. Fill other fields with valid data. 4. Click "Send".
Env: Staging
Module: Contact Form
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_09_Invalid_Email_Format.png
Expected: Should show error message "Please enter a valid email address".
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 03
Issue: No success or failure message shown after contact form submission with valid data.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/contact-us 2. Fill all fields with valid data. 3. Select a budget option. 4. Click "Send".
Env: Staging
Module: Contact Form
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_06_No_Success_Message.png
Expected: Should show a success message "Your message has been sent successfully".
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 04
Issue: Footer "Articles" link returns a 404 Not Found error page.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ 2. Scroll down to the footer section. 3. Click on the "Articles" link.
Env: Staging
Module: Footer
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_11_Footer_Articles_404.png
Expected: Should redirect to the Articles page with article content.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 05
Issue: Footer newsletter Subscribe does not validate blank or invalid email input.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ 2. Scroll to the footer. 3. Leave the email field blank. 4. Click the "Subscribe" button.
Env: Staging
Module: Footer
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_12_Footer_Subscribe_No_Validation.png
Expected: Should show a validation error "Please enter a valid email address".
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 06
Issue: Privacy Policy and Terms & Conditions links are missing from the footer.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ 2. Scroll to the footer section. 3. Look for Privacy Policy and Terms & Conditions links.
Env: Staging
Module: Footer
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_13_Missing_Privacy_Terms.png
Expected: Both Privacy Policy and Terms & Conditions links should be present in the footer.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 07
Issue: Services dropdown menu appears behind hero section content on Safari browser.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ in Safari. 2. Hover over or click "Services" in navigation bar. 3. Observe if dropdown appears above all page content.
Env: Staging
Module: Navigation
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_01_Services_Dropdown_Safari.png
Expected: Dropdown should appear on top of all page content in all browsers.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 08
Issue: Footer columns overlap each other at 375px mobile viewport. Layout is broken.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ 2. Set browser viewport to 375px. 3. Scroll down to the footer section.
Env: Staging
Module: Footer ¦ Responsive
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_21_Footer_Overlap_375px.png
Expected: Footer columns should stack vertically into a single column on mobile viewport.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 09
Issue: Hero section text overflows the container and causes horizontal scroll at 320px.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ 2. Set browser viewport to 320px. 3. Check the hero section heading and subtext.
Env: Staging
Module: Homepage ¦ Responsive
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_20_Hero_Overflow_320px.png
Expected: All text should remain within the viewport. No horizontal scrollbar should appear.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 10
Issue: Page Lighthouse performance score ~52 on mobile. FCP is 4.2s and TBT is ~600ms.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ in Chrome. 2. Open DevTools > Lighthouse tab. 3. Select Mobile and Performance. 4. Click "Analyze page load".
Env: Staging
Module: Performance
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_27_Lighthouse_Score_Mobile.png
Expected: Performance score should be 90+. FCP under 1.8s. TBT under 200ms.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 11
Issue: All images load on initial page load. No lazy loading implemented for below-fold images.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ in Chrome. 2. Open DevTools > Network tab. 3. Filter by "Img". 4. Reload page and observe all images loading at once.
Env: Staging
Module: Performance
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_28_No_Lazy_Loading.png
Expected: Below-fold images should only load when user scrolls near them.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 12
Issue: 3 JavaScript errors and 1 resource 404 error appear in console on every page load.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ in Chrome. 2. Open DevTools > Console tab. 3. Reload the page. 4. Count all errors shown.
Env: Staging
Module: Performance
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_29_Console_JS_Errors.png
Expected: Zero console errors should appear on a clean page load.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 13
Issue: Hamburger menu does not close when user taps outside the menu panel on mobile.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ 2. Set viewport to 375px. 3. Tap the hamburger icon to open menu. 4. Tap anywhere outside the menu panel.
Env: Staging
Module: Navigation ¦ Mobile
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_03_Hamburger_Outside_Tap.png
Expected: Menu should close when user taps anywhere outside the menu panel.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 14
Issue: Testimonials section causes horizontal overflow and scrollbar appears at 768px tablet.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/ 2. Set viewport to 768px. 3. Scroll to the testimonials section.
Env: Staging
Module: Homepage ¦ Responsive
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_23_Testimonials_Overflow_768px.png
Expected: All sections must fit within 768px viewport without horizontal overflow.
Responsible QA: MD Mahedy hasan Naiem
Bug Reporting
# SL 15
Issue: Active page not highlighted in navigation bar. All links look identical on every page.
Reproducing Steps:
1. Goto the URL https://staging.qtecsolution.com/about-us 2. Check if the "About Us" link looks different from other nav links.
Env: Staging
Module: Navigation
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: SS_BUG_05_Nav_Active_State.png
Expected: Current page link should be visually highlighted (underline or color change).
Responsible QA: MD Mahedy hasan Naiem